## Sprint Journal
Wesley shih | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Designed High Level Architecture Diagram Updated Weekly Scrum Report and Sprint Journal Decided tech stack with the team
|  | What am I planning to do to next? | Setting up AWS RDS for Db and Develop base project and share with team
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Created Databse Server and Developed APIs for Login, Signup and fronted for the same
|  | What am I planning to do to next? | Develop API calls for Userdashboard and work on frontend
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Developed API Calls for UserDashboard: for enrolling into classes, log activities, view classes and activities
|  | What am I planning to do to next? | Develop frontend part of the userdashboard
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Developed frontend part of the userdashboard
|  | What am I planning to do to next? | Bug fixes and flow integration
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Updated API calls and frontend code as part of bug fixes and flow integration
|  | What am I planning to do to next? | Deploy Application in AWS EC2
|  | What tasks are blocked waiting on another team member? | None
Nohar | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Designed portion of UI Wireframes Updated Weekly Scrum Report Updated Sprint Journal
|  | What am I planning to do to next? | Understand how to develop API for Users dashboard to view their activities
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Started to develop API for Users dashboard to view their activities
|  | What am I planning to do to next? | Complete the development API for Users dashboard to view their activities
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Developed the API for Users dashboard to view their activities
|  | What am I planning to do to next? | Develop front end UI for user dashboard
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Developed the front end UI for user dashboard
|  | What am I planning to do to next? | Bug Fixes and minor changes.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Bug Fixes and minor changes.
|  | What am I planning to do to next? | Complete the Readme for the project.
|  | What tasks are blocked waiting on another team member? | None
Ram Sai | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Updated Weekly Scrum Report Updated Sprint Journal
|  | What am I planning to do to next? | Develop admin backend DB queries
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Develop admin backend DB queries and create necessary DB tables
|  | What am I planning to do to next? | Develop admin console for user information
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Develop and test admin console for user information
|  | What am I planning to do to next? | Develop and test pop up form for checking in and checking out users to health club
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Develop and test pop up form for checking in and checking out users to health club
|  | What am I planning to do to next? | Develop and test pop up form for enrolling new members to the health club
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Develop and test pop up form for enrolling new members to the health club
|  | What am I planning to do to next? | Test and fix any bugs in app and prepare documentation
|  | What tasks are blocked waiting on another team member? | None
Murali Monish Addagarla | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Designed portion of UI Wireframes Updated Weekly Scrum Report Updated Sprint Journal
|  | What am I planning to do to next? | Setup React app, create a basic react component and Develop API for landing page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Create a basic react component and Developed API to access landing page after setting up the react app
|  | What am I planning to do to next? | Enhance the apis of landig page to make it dynamic to the choice of location selected
|  | What tasks are blocked waiting on another team member? | Accessing list of locations where the gyms are available requires data from database, which has to be populated
| Sprint 3 | What task did I work on/complete? | Populated locations dropdown with data from db. Displayed memberships & classes according to selected location
|  | What am I planning to do to next? | Creation of Cards component to display both the memberships and classes data, associated with a flip functionality
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Implemented cards with desired functionality on the landing page
|  | What am I planning to do to next? | Develop AdminDashboard with 2 components to enter selection criteria and the other to visually present the data for given entries
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | implemented charts component which helps in analysing data on particular dates and locations
|  | What am I planning to do to next? | Deploy Application in AWS EC2
|  | What tasks are blocked waiting on another team member? | None